## Sheet1
Reference No. | Priority | Risk Name | Risk Description | Cause | Dependent Systems | Risk Owner (POC) | Priority (Impact/Likelihood) | Cost | Risk Treatment | Control | Residual Risk | Accepted Y/N
SI - 7 | Significant | IT | Patient's Medical App access tool could be hacked resulting in loss of customer information | App is vulnerable to malicious attacks due to lack of two factor authentication(MFA) |  | Ms.Digger CIO | High | >$950,000 | Application Testing,Pen Testing , Adding MFA option for all accounts | AC-4, CM-3 , CM -7 | Not acceptable | Yes
SI-4(17) | Moderate | Accounting/Finance | Patients who pay with their debit/credit cards on file to pay off their outstanding medical bill amount is vulnerable to having their debit/credit card information stolen if the patient PII(Personal Identifiable Information)is hacked | Unsecure website which is prone to vulnerable attacks by hackers to gain personal information of patients |  | Mr.Chewer | Medium | <$800,000 | Daily monitoring of SIEM to eliminate threats from a hacker who is trying to gain personal info of patients. | AU-16, SR-2 , SR-6 | Not acceptable | Yes
SI-4(19) | Minor | Legal Counsel | Patients who were not satisfied with their medical treatment could post hateful comments or proceed with legal counsel if their medical procedure was not satifactory or did not go as planned / as discussed by the organization staff to the patient before the treatment was undergone .They could also file a lawsuit if they were involved in a data breach / malware attack by using the organization's app/website | Hateful comments by patients in social media such as Facebook or Twitter / Faced by court proceedings due to unforeseen failed medical procedures done by the medical staff |  | Mr.Clicker CLO | Low | <$200,000 | Compliance and training departments work closely to monitor pending legislation and quickly adjust training and compliance programs as needed | None. | Residual Risk is acceptable | Yes